## Team 13
Week | Task | Description | Time Spent (hrs) | Weekly Total
1/9 - 1/15 | Documentation | Work on Vision document by assigning task to all the requirents. | 30 | 56
| Setup Tools | Slack, Taiga, GitHub Created new Stories in Taiga for all the Requirements. Created Tasks in Taiga for each of the user stories. | 4
| Feedback | Gather feedback from SDS , SRS , Project charter and Project plan, and work on improvement. | 22
1/16 - 1/22 | Code | Started working on creating a Java Swing prototype. Designed the workflow of swing app to look have a user interface similar to that of a mobile screen. Deduce the best way forward to write the code in swift, options were to use a conveter or write from scratch. Understand the time required and limitations in both the method. Performed a research on the database issue, did gradle upgrades and tried different versions to resolve the database issues. Built the initial screens as modeled in the prototype. Created a JFrame for user to enter username and password. Implemented a call back method to validate the user. | 31 | 53.5
| Research | Researched different converters and plug in available for xcode which helps in converting in Objective-C to swift. Choose between converting the code or writing from scratch. Researched on the database issue in the Android Application | 17
| Team Meeting | Had a meeting with customer and sponsor and discussed on the requirements for Android App and Server Side integration. Discussed with the team and the sponsor on the web server. Communicated the requirements of the server space required. | 5.5
1/23 - 1/29 | Code | Created User Interface to perform User Authentication to log into the app. Created JFrames and JPanel to have several buttons such as 'news and events', 'field notes' etc. Implemented button listener to enable navigation from one JFrame to another. Using converter to build one functionality of the iOS application, this was our feasibility testing. Incorporate the images and links provided by Julie Russ in the code base. Performed a research on the database issue, did gradle upgrades and tried different versions to resolve the database issues. Built the initial screens as modeled in the prototype. Created a JFrame for user to enter username and password. Implemented a call back method to validate the user. Created a form to send the details entered by the user to the server. | 53.5 | 57.5
| Sponsor Meeting | Discussed the research with Professor Lindquist and then zeroed down on one converter swiftify. Received the new application guide for building the app from the sponsor. Had a meeting with customer to showcase on the weekly progress and to discuss on the next steps | 4
1/30 - 2/5 | Sponsor Meeting | Effort required form the converter was too much , discussed this with sponsor and decide to go ahead by writing code from scratch in swift . Obtained the server details from the sponsor.Demonstrated the app to the client, the sponsor and the team to receive feedback on the same. discuss on the database issues on android app and using of JSON instead of XML to transfer the information content. | 4.5 | 55.5
| Code | Going ahead we will be starting a new project and will seek help from objective - c code. Create Independent JFrames for serveral individual screens such as 'News and Events', 'Field Notes', 'Donate Page', 'Gallery', 'About Page', 'Connect'. Implemented Card Layout to mimik mobile screen for each of these individual JFrames. Created JList for Field Notes and News and Events to display the list of event and news. Perfomed code refactoring for DBHelper file to fix the issue with database. Database Issue got fixed. Performed an analysis to resolve the navigation issue, specially while navigating back from screen ("News and Events"). Started working on sending the data submitted to the server in JSON format. | 51
2/6 - 2/13 | Code | Working on Navigation Controls in Android App. Performing research to fix the issue, wherein clicking device's "Back" button messes up the information content. Implemented button listeners to peform appropriate user actions. Provided buttons to edit, view and delete the individual list items. Created Frames to display individaul list items from News and Events and Filed Notes page. Completed working on coding in swift 3 for About and Donation functionality. Working on Navigation controls and overall layout of app. Continue work on Main Page. Completed start work on News and Events Page with static table view Proceed with coding for submitting the data to the sevrer. | 59 | 59
2/13 - 2/19(Ongoing) | Code | Started working on NewsViewController. Connected to server and fetched JSON. Parsed JSON and showed the latest news in News Tableview. Configured Server. Created and Pushed JSON for news to server Working on completing "Connect to IHO" button. Worked on a) fetching demo JSONObject for "News" from the server b) Parsing JSON and converting into "News" Model class c)Displaying as News List and News Info. Fixing issues with editing travel content, adding links etc | 47 | 53
| Documentation | Code Report and Software Demo Report (Android + iOS + Swing) | 2

## Sweta
Week | Task | Task | Time Spent (hrs) | Weekly Total
01/09 - 01/15 | Feedback | Worked on the feedback of previous semester. Worked on restructioning of documents. | 4 | 12
| Vision Document | Worked on Vision document. Created class diagram for iOS and Android for Vision document and Software Design Specification. | 7.5
01/16 - 01/22 | Meeting | Scheduled meeting with customer (Julie Russ) and sponsor (Dr. Lindquist) | 0.5
| Research | Researched different converters and plug in available for xcode which helps in converting in Objective-C to swift. | 4 | 13
| Setup Tools | Worked on Taiga, Github, Slack | 2
| Code | Tried the different converters. Deduce the best way forward to write the code in swift, options were to use a conveter or write from scratch. Understand the time required and limitations in both the methods. | 7
01/23 - 01/29 | Sponsor Meeting | Discussed the research with Professor Lindquist and then zeroed down on one converter swiftify. | 1 | 13
| Code | Using converter to build one functionality of the iOS application, this was our feasibility testing. Incorporate the images and links provided by Julie Russ in the code base. | 12
01/30 - 02/05 | Sponsor Meeting | Effort required form the converter was too much , discussed this with sponsor and decide to go ahead by writing code from scratch in swift . | 1 | 16
| Code | Going ahead we will be starting a new project and will seek help from objective - c code. Started with MainViewController and Main page. | 15
02/06 - 02/12 | Code | Working on Navigation controls and overall layout of app. Continue work on Main Page. Completed start work on News and Events Page with static table view | 15 | 15
2/13 - 2/19(Ongoing) | Code | Started working on NewsViewController. Connected to server and fetched JSON. Parsed JSON and showed the latest news in News Tableview | 15 | 16
| Document | Code Report and Demo Report (iOS) | 1

## Gowtham
Week | Task | Task | Time Spent (hrs) | Weekly Total
01/09 - 01/15 | Feedback and Vision Document | Worked on revising the document based on feedback received. | 8 | 12
| Tiaga | Created User Stories in Tiaga for all the requirements documented in the Software Requirements Specification Document. Created Tasks in Taiaga for each of the user stories. | 2
| Design | Designed a prototype for the User Interface. Modeled the workflow between various user screens. | 2
01/16 - 01/22 | Meeting | Discussed with the team and the sponsor on the web server. Communicated the requirements of the server space required. | 2 | 11
| Code | Built the initial screens as modeled in the prototype. Created a JFrame for user to enter username and password. Implemented a call back method to validate the user. | 9
01/23 - 01/29 | Code | Created JFrames and JPanel to have several buttons for 'News and Events', 'Field Notes','Gallery', 'About', 'Donate', 'Connect' | 4.5 | 13.5
| Research | Researched on the components available in Swing to see if user can stay within a JFrame without moving to a differerent frame while moving from one screen to another. | 1.5
| Code | Implemented button listener to enable navigation from one JFrame to another. | 5
| Test | Tested implementing Card Layout. Because code was getting cluttered in a single class and was performing unrelated operations, created new JFrames for individual functional components. | 2.5
01/30 - 02/05 | User Interface | Created independent JFrames for serveral individual screens to hold their own content. JFrames were created for the following 'News and Events', 'Field Notes', 'Donate Page', 'Gallery', 'About Page', 'Connect'. | 5 | 12
| Code | Implemented Card Layout to mimik mobile screen for each of these individual JFrames. Created a container panel and set of individual panels for each of the three buttons in 'News and Events' and 'Field Notes' | 3.5
| Code | Created JList for Field Notes and News and Events to display the list of events and news. | 2
| Test | Tested each of the above componenets to see that they are functioning correctly. | 1
| Meeting | Demonstrated the app to the client, the sponsor and the team to receive feedback on the same. | 0.5
2/6 - 2/12 | Code | Created Frames to display individaul list items from News and Events and Filed Notes page. | 3.5 | 11
| Code | Provided buttons to edit, view and delete the individual list items. | 0.5
| Code | Implemented button listeners to peform appropriate user actions. | 7
2/13 - 2/19(Ongoing) | Code | Configured Server. Created and Pushed JSON for news to server | 16 | 16

## Arpit
Week | Task | Description | Time Spent (hrs) | Weekly Total
1/9 - 1/15 | Vision Document | Work on completion of Vision Document | 7 | 11
| Setup Tools | Slack, Taiga, GitHub | 1
| Feedback | Work on feedback given in 517 | 3
1/16 - 1/22 | Research | Choose between converting the code or writing from scratch | 9 | 10
| Sponsor Meeting | Discussion on Server and other application requirement | 1
1/23 - 1/29 | Code | Converter to cpme with Swift 3 app(feasibility testing) | 10 | 11
| Requiremnt Gathering | Incorporate new images in the codebase as provide by sponsor | 1
1/30 - 2/5 | Sponsor Meeting | Effort required form the converter was too much , discussed this with sponsor and decide to go ahead by writing code from scratch in swift . | 1 | 11
| Code | Build functionality of two buttons(About & Donate) in swift 3 seeking design help from previous application. | 10
2/6 - 2/12 | Code | Completed working on coding in swift 3 for About and Donation functionality. | 11 | 11
2/13 - 2/19 (on going) | Code | Working on completing "Connect to IHO" button. | 3 | 3

## Mihir
Week | Task | Task | Time Spent (hrs) | Weekly Total
01/09 - 01/15 | Feedback | Collaborated with the team mates and worked on the previous semester's feedback for Software Design Specification. | 4 | 11
| Vision Document | Contributed to Vision document. Created class diagram for Android for Vision document and decided on the requirements and tasks for each demo. | 7
01/16 - 01/22 | Meeting | Had a meeting with customer and sponsor and discussed on the requirements for Android App and Server Side integration | 1
| Research | Researched on the database issue in the Android Application | 4 | 11
| Setup Tools | Worked on setting up Taiga and Github for the project | 1
| Code | Performed a research on the database issue, did gradle upgrades and tried different versions to resolve the database issues. | 6
01/23 - 01/29 | Sponsor Meeting | Had a meeting with customer to showcase on the weekly progress and to discuss on the next steps | 1 | 13
| Code | Continued research on the database issue. Found couple of version issues. Identified code which required code refactoring. Also, found and analysed the navigation issue in the android app. | 12
01/30 - 02/05 | Sponsor Meeting | Had a meeting with customer to showcase on the weekly progress, discuss on the database issues on android app and using of JSON instead of XML to transfer the information content. | 1 | 12
| Code | Perfomed code refactoring for DBHelper file to fix the issue with database. Database Issue got fixed. Performed an analysis to resolve the navigation issue, specially while navigating back from screen ("News and Events"). | 11
02/06 - 02/12 | Code | Working on Navigation Controls in Android App. Performing research to fix the issue, wherein clicking device's "Back" button messes up the information content. | 10 | 10
02/13 - 02/19 | Code | Worked on a) fetching demo JSONObject for "News" from the server b) Parsing JSON and converting into "News" Model class c)Displaying as News List and News Info | 11 | 11.5
| Document | Contributed to Software Demo report (Android) | 0.5

## Sindhu
Week | Task | Description | Time Spent (hrs) | Weekly Total
1/9 - 1/15 | Vision Document | Worked on the vision document | 6 | 10
| Setup Tools | Slack, Taiga, GitHub | 1
| Feedback | Worked on feedback given for the previous semester. Created class diagram for the Swing application | 3
1/16 - 1/22 | Code | Started working on the Swing application Started implementing the functionalities for each user screen. | 9 | 10
| Sponsor Meeting | Discuss the server requirements with the sponsor | 1
1/23 - 1/29 | Code | Created a form to send the details entered by the user to the server. | 10 | 11
| Sponsor Meeting | Received the new application guide for building the app from the sponsor | 1
1/30 - 2/5 | Sponsor Meeting | Obtained the server details from the sponsor. | 1 | 11
| Code | Started working on sending the data submitted to the server in JSON format. | 10
2/6 - 2/13 | Code | Proceed with coding for submitting the data to the sevrer. | 11 | 11
2/14-2/19 | Code | Fixing issues with editing travel content, adding links etc | 5 | 5.5
| Document | Demo Report (Swing) | 0.5
Total Hours
46
Average Hours/Week
4.1818